## Organisation
Scrumorganisation
Teammembers | Rolle | Email
Ivan Wissler | Developer | wissi1@bfh.ch
Michael Heeb | Developer / Master | heebm2@bfh.ch
Faton Shabanaj | Developer | shabf2@bfh.ch
Ranjit Kalarickamakel | Developer | kalar1@bfh.ch
Patrizia Zehnder | Developer | zehnp1@bfh.ch
Swetlana Sianko | Developer | sians1@bfh.ch
Jürgen Vogel | product owner | uergen.vogel@bfh.ch
Scrummeeting | Zeit | Ort
Mittwoch | 16:15 | 421
Freitag | 10:00 | 506

## Product Backlog
ID | Story Name | Description | Priority | Effort Estimate | Effort Actual | Status
1 | Login success | Authorized User wants to login | high |  |  | waiting
2 | Login failure | Unauthorized User wants to login | high |  |  | waiting
3 | Password Wrong | User tries to login with wrong password | medium |  |  | waiting
6 | Medication Info Search | User wants to search info for specific medication |  |  |  | waiting
7 | Desiase Info Search | User wants to search info for specific desiase |  |  |  | waiting
8 | Kommentar Add |  |  |  |  | waiting
9 | Kommentar Delite |  |  |  |  | waiting
10 | Edit Kommentar |  |  |  |  | waiting
11 | [5 empty] | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Estimate | Effort Spent | Effort Remaing | Effort Actual | Status
1.1 | 1 | Package Diagram | UML Package Diagram |  | shabf2 | high | 4
1.9 | 1 | Class Organisation | Packages and Class and navigator Creation |  | wissi1 |  |  | 3 |  |  | finished
1.2 | 1 | GUI Login | Build GUI for Login | View | shabf2 | high | 5 |  |  |  | waiting
1.3 | 1 | GUI Home | Build GUI for Home | View | shabf2 | high | 5 |  |  |  | waiting
1.4 | 1 | GUI Search view (Medi) | Build GUI for Medi Search | View | sians1 | high | 5 |  |  |  | waiting
1.5 | 1 | GUI Search view (Disease) | Build GUI for Disease Search | View | zehnp1 | high | 5 |  |  |  | waiting
1.6 | 1 | GUI Browse Medi Info | Build GUI for Medi Info | View | kalar1 | high | 5
1.7 | 1 | GUI Browse Disease Info | Build GUI for Disease Info | View | wissi1 | high | 5
1.8 | 1 | GUI Komment view | Build GUI for Komment view | View | heebm2 | high | 5
2 | 1 | Database | Create DB, Access | Database |  |  | 3 |  |  |  | waiting
2.1 | 2 | search medication info | search info for specific medication | Model/Database |  |  | 4 |  |  |  | waiting
2.2 | 2 | browse medication info | get a info of medication | Model/Database |  |  | 5 |  |  |  | waiting
3.1 | 3 | search disease info | search info for specific disease | Model/Database |  |  | 4 |  |  |  | waiting
3.2 | 3 | browse disease info | get a info of disease | Model/Database |  |  | 5 |  |  |  | waiting
4.1 | 4 | write/add kommentar | save data in record | Model/Database |  |  | 5 |  |  |  | waiting
4.2 | 4 | delite kommentar |  | Model/Database |  |  | 5 |  |  |  | waiting
4.3 | 4 | edit kommentar |  | Model/Database |  |  | 5 |  |  |  | waiting

## Burndown Chart
Task | Start | Meeting 1 | Meeting 2 | Meeting 3 | Meeting 4 | Meeting 5 | Meeting 6 | Meeting 7 | Meeting 8 | Meeting 9 | Meeting 10
1.1 | 4 | 3
1.2 | 5
1.3 | 5
1.4 | 5
1.5 | 3
2 | 4
2.1 | 5
2.2 | 4
3.1 | 5
3.2 | 5
4.1 | 5
4.2 | 5
4.3 | 0
0 | 0
0 | 0
Optimal | 55
Effektiv