## Organisation
Scrumorganisation
Teammembers | Rolle | Email
Ivan Wissler | Developer | wissi1@bfh.ch
Michael Heeb | Developer / Master | heebm2@bfh.ch
Faton Shabanaj | Developer | shabf2@bfh.ch
Ranjit Kalarickamakel | Developer | kalar1@bfh.ch
Patrizia Zehnder | Developer | zehnp1@bfh.ch
Swetlana Sianko | Developer | sians1@bfh.ch
Jürgen Vogel | product owner | uergen.vogel@bfh.ch
Scrummeeting | Zeit | Ort
Mittwoch | 16:15 | 421
Freitag | 14:20 | 506

## Product Backlog
ID | Story Name | Description | Priority | Effort Estimate | Effort Actual | Status
1 | Login success | Authorized User wants to login | high |  |  | waiting
2 | Login failure | Unauthorized User wants to login | high |  |  | waiting
3 | Password Wrong | User tries to login with wrong password | medium |  |  | waiting
6 | Medication Info Search | User wants to search info for specific medication |  |  |  | waiting
7 | Desiase Info Search | User wants to search info for specific desiase |  |  |  | waiting
8 | Kommentar Add |  |  |  |  | waiting
9 | Kommentar Delite |  |  |  |  | waiting
10 | Edit Kommentar |  |  |  |  | waiting
11 | [5 empty] | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Estimate | Effort Spent | Effort Remaing | Effort Actual | Status
1.1 | 1 | Package Diagram | UML Package Diagram |  | shabf2 | high | 4 | 4 |  |  | finished
1.2 | 1 | GUI Login | Build GUI for Login | View | shabf2 | high | 5 | 4.5 |  |  | finished
1.3 | 1 | GUI Home | Build GUI for Home | View | shabf2 | high | 5 | 5 |  |  | finished
1.4 | 2 | GUI Search view (Medi) | Build GUI for Medi Search | View | sians1 | high | 5 | 5 |  |  | finished
1.5 | 2 | GUI Search view (Disease) | Build GUI for Disease Search | View | zehnp1 | high | 5 | 5 |  |  | finished
1.6 | 2 | GUI Browse Medi Info | Build GUI for Medi Info | View | kalar1 | high | 5 | 4 |  |  | finished
1.7 | 2 | GUI Browse Disease Info | Build GUI for Disease Info | View | wissi1 | high | 5 | 7 |  |  | finished
1.8 | 1 | GUI Komment view | Build GUI for Komment view | View | heebm2 | high | 5 | 6 |  |  | finished
1.9 | 1 | Navigation planung | State Patten |  | heebm2, wissi1 | high | 7 | 7 |  |  | finished
2 | 2 | Comment | Java Doc comment |  | all |  | 0.5 | 0.5 |  |  | waiting
2.1 | 2 | Testing |  |  | all |  | 1 | 0.5 |  |  | finished
0
3.1 | 3 | XML Users | Create XML-File and Schema | Database | shabf2 | medium | 6 | 0 |  |  | waiting
3.2 | 3 | XML Medicaments | Create XML-File and Schema | Database | zehnp1 | medium | 6 | 0 |  |  | waiting
3.3 | 3 | XML Diseases | Create XML-File and Schema | Database | zehnp1 | medium | 6 | 0 |  |  | waiting
3.4 | 3 | XML Comments | Create XML-File and Schema | Database | sians1 | medium | 6 | 0 |  |  | waiting
3.5 | 3 | load/update data | read and overridde XML-Files | Database | wissi1 | high | 5 | 0 |  |  | waiting
3.6.1 | 3 | search medication info | search info for specific medication | Model/Database | heebm2 | high | 8 | 0 |  |  | waiting
3.6.2 | 3 | search disease info | search info for specific disease | Model/Database | heebm2 | high | 8 | 0 |  |  | waiting
3.7 | 3 | login | check login information | Model/Database | shabf2 | high | 8 | 0 |  |  | waiting
3.8.1 | 3 | search comments | search and display comment data in XML | Model/Database | wissi1 | high | 6 | 0 |  |  | waiting
3.8.2 | 3 | write comments | write new comment data in XML | Model/Database | kalar1 | high | 6 | 0 |  |  | waiting
3.9 | 3 | Testing |  |  | all |  | 2 | 0 |  |  | waiting

## Burndown Chart
|  | 29.11 | 4.12 | 6.12 | 10.12 | 13.12 | 18.12 | 20.12
Task | Start | Meeting 1 | Meeting 2 | Meeting 3 | Meeting 4 | Meeting 5 | Meeting 6 | Meeting 7 | Meeting 8 | Meeting 9 | Meeting 10
1.1 | 4 | 4
1.2 | 5 | 2 | 2 | 0.5
1.3 | 5 | 1 | 2 | 2
1.4 | 5 | 1 | 2 | 2
1.5 | 5 | 1 | 2 | 2
1.6 | 5 | 1 | 2 | 1
1.7 | 5 | 4 | 2 | 1
1.8 | 5 | 2 | 3 | 1
1.9 | 7 |  | 3 | 3 | 1
2 | 0.5 |  |  |  | 0.5
2.1 | 1 |  |  |  |  | 0.5
0 | 0
3.1 | 6
3.2 | 6
3.3 | 6
3.4 | 6
3.5 | 5
3.6.1 | 8
3.6.2 | 8
3.7 | 8
3.8.1 | 6
3.8.2
Optimal | 106.5
Effektiv | 48.5